## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | GK - 6/25/19 | Pass | IFB 7/18/19
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. |  | GK - 6/25/19 | Pass | IFB 7/18/19
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. |  | GK - 6/25/19 | Fail | No spaces were accepted by the game | Pass | GDK 7/25/19
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. |  | GK - 6/25/19 | Pass | IFB 7/18/19
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. |  | GK - 6/25/19 | Pass | IFB 7/18/19
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | GK - 6/25/19 | Pass | IFB 7/18/19
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | GK - 6/25/19 | Pass | IFB 7/18/19
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  | GK - 6/25/19 | Pass | IFB 7/18/19
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  | GK - 6/25/19. | Pass | IFB 7/18/19
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | GK - 6/25/19 | Pass | IFB 7/18/19
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  | GK - 6/25/19 | Pass | IFB 7/18/19
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  |  | Pass | IFB 7/18/19
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  |  | Pass | IFB 7/18/19
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  |  | Pass | IFB 7/18/19
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  |  | Pass | IFB 7/18/19
As a Player I want to play my turn so that I can move my pieces around the board. | Given the Game is not over, When it is my turn, Then I should be able to move my pieces and play my turn. |  |  | Pass | IFB 7/18/19
| Given the Game is not over When it in not my turn Then I must wait for my opponent to take their turn. |  |  | Pass | IFB 7/18/19
| Given the Game is over When I choose to exit the Game Then I will be redirected to the lobby. |  |  | Pass | IFB 7/18/19
| Given that it is my turn When I make a move Then the server should validate my move. |  |  | Pass | IFB 7/18/19
| Given that my move is valid When I submit the move Then the server updates the Game with it. |  |  | Pass | IFB 7/18/19
| Given that my move is valid When I choose to revert the move, Then I should be able to try another move. |  |  | Pass | IFB 7/18/19
| Given that my move is not valid When the move is rejected Then I should be able to try another move. |  |  | Pass | IFB 7/18/19
| Given I am in a game When I have not made a move Then I should have the option to resign. |  |  | Pass | IFB 7/18/19
| Given that I want to resign When I click the resign button Then the Game will end. |  |  | Pass | IFB 7/18/19
As a Player I want to wait for my opponent to play their turn so that we have a fair match. | Given I am in a game When it is my turn Then I should have the option to move my pieces around the board. |  |  | Pass | IFB 7/18/19
| Given that it is not my turn When the page refreshes Then the application should check if it is now my turn. |  |  | Pass | IFB 7/18/19
| Given that I am in a game When I am waiting for my opponent, Then I should have the option to resign. |  |  | Pass | IFB 7/18/19
| Given that I want to resign When I click the resign button Then the Game will end. |  |  | Pass | IFB 7/18/19
As a Player I want to resign because I know I'm going to lose. | Given two players are playing When one player hits the Resign button Then the game is over |  |  | Pass | IFB 7/18/19
| Given that it is not my turn, when I click the resign button, then I will be taken back to the home page. |  |  | Pass | IFB 7/18/19
| Given that it is not my turn, when my opponent clicks the resign button, then I will be notified of their resignation. |  |  | Fail | One player clicked resign, then the second player also clicked resign, but the first player had already resigned, so it broke | Pass | GDK 7/25/19
| Given that it is my turn, when I click the resign button, then I will be taken back to the home page. |  |  | Pass | IFB 7/18/19
| Given that it is my turn, when my opponent resigns and after I finish my turn, then I will be notified of their resignation. |  |  | Pass | IFB 7/18/19
As a Player I want to sign out because I'm done playing. | Given a player is logged in When the sign out button is pressed Then the player is signed out |  |  | Pass | IFB 7/18/19
| Given a player is signed out When the page refreshes Then the sign in option should be available again |  |  | Pass | IFB 7/18/19
As a Player I want to know when the game is over so that I can move on to other games. | Given that there are no additional turns/moves possible, When the final Game board is displayed, Then I can see a message detailing how the game ended. |  |  |  |  | Pass | GDK 7/25/19
| Given that the Game is over, When I see the final Game board, Then I should have a means to exit the game and return home. |  |  |  |  | Pass | GDK 7/25/20
| Given that I want to resign, When I click the resign button, Then the Game should stop and display the end game message. |  |  |  |  | Pass | GDK 7/25/21
As a Player I want to move my pieces so that I can win the game. | Given that it is my turn, When I drag a piece onto a valid square, Then I should be able to submit my turn. |  |  |  |  | Pass | GDK 7/25/22
| Given that it is my turn, When I drag a piece onto an invalid square, Then the piece should return to its original position and I should be shown an error message. |  |  |  |  | Pass | GDK 7/25/23
As a Player I want to jump over my opponent's pieces so that I can win the game. | Given that it is my turn, When one of my pieces is able to jump over an opponent piece, Then I am able to take that jump. |  |  |  |  | Pass | GDK 7/25/24
| Given that it is my turn, When I have multiple jump moves available, Then I can choose between them. |  |  |  |  | Pass | GDK 7/25/25
As a Player I want to jump over multiple pieces so that I can crush my opponent's self-esteem. | Given that it is my turn, when a multi-jump move is available, Then I must move my piece along that path. |  |  |  |  | Pass | GDK 7/25/26
| Given that it is my turn, When multiple multi-jump paths are available, then I can choose which one I want to use. |  |  |  |  | Pass | GDK 7/25/27
As a Player I want to get king pieces so that I can move in any direction. | Given it is a Player's turn, When a piece reaches the king row, Then the piece should be promoted to a king. |  |  |  |  | Pass | GDK 7/25/28
| Given a piece is a king, When the king piece is moving, Then the king piece has the option to go forward or backward. |  |  |  |  | Pass | GDK 7/25/29